## Tools
id | name | category | status | impact | description | notes | w1Date | targetEndDate | flaggedProgressWeek | owners
1 | HSD Conversion | hsd | In Progress | High | Automated conversion of HSD artifacts to target format using AI |  | 2025-01-06 | 2025-04-14 |  | Akhil
2 | Selenium Test Generation | selenium | In Progress | High | AI-assisted Selenium test case generation via Windsurf + BT1 MCP server |  | 2025-01-06 | 2025-05-05 |  | Akhil
3 | Playwright Conversion | playwright | Planning | Medium | Convert Selenium/manual test suites to Playwright via AI-assisted migration |  | 2025-02-03 | 2025-05-26 |  | Akhil
4 | Dummy project | dummy | Complete | Low | Test |  | 2025-03-03 | 2025-05-26 |  | Abhilasha

## Milestones
tool_id | id | label | week | done | targetDate
1 | m1 | Discovery & scoping | 1 | TRUE
1 | m2 | Prototype ready | 4 | TRUE
1 | m3 | Internal review | 7 | FALSE
1 | m4 | Team rollout | 10 | FALSE
2 | m5 | MCP server integration | 1 | TRUE
2 | m6 | XPath accuracy fix | 3 | TRUE
2 | m7 | Demo to stakeholders | 5 | TRUE
2 | m8 | XPath automation | 8 | FALSE
2 | m9 | Git integration | 11 | FALSE
3 | m10 | Scope & feasibility | 2 | FALSE
3 | m11 | Conversion prototype | 6 | FALSE
3 | m12 | Pilot on 1 test suite | 9 | FALSE
3 | m13 | Full rollout | 13 | FALSE

## Subtasks
tool_id | id | label | done
1 | s1 | Define input/output schema | TRUE
1 | s2 | Build AI parsing layer | TRUE
1 | s3 | Error handling & edge cases | FALSE
1 | s4 | QA & validation pass | FALSE
2 | s5 | Story/defect input parsing | TRUE
2 | s6 | Reliable XPath capture via Selenium IDE | TRUE
2 | s7 | Automate XPath recording | FALSE
2 | s8 | Git integration for test export | FALSE
3 | s9 | Audit existing Selenium suite | FALSE
3 | s10 | Define Playwright target format | FALSE
3 | s11 | Build AI conversion script | FALSE
3 | s12 | Validate converted tests | FALSE